## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For Students
ⓒ2021 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  |  |  | 2023-07-30
Project Team Name |  |  |  | Ruba, Sara, Ghassan, Meshal, Martada, Abdullah
Project Topic
Task |  |  |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[10 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[10 empty] | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-20
1. Brainstorming ideas |  |  |  |  | 2023-07-20 | 2023-07-25 | All |  | Done | bar: 2019-01-01 to 2019-01-13
| 1.1. Research |  |  |  | 2023-07-20 | 2023-07-29 | All |  | Done | bar: 2019-01-01 to 2019-01-12
|  | 1.1.1. Evaluation |  |  | 2023-07-29 | 2023-07-30 | All |  | Done | bar: 2019-01-01 to 2019-01-08
|  |  | 1.1.1.1. Planing |  | 2023-07-30 | 2023-07-30 | All |  | Done | bar: 2019-01-01 to 2019-01-08
|  |  |  | 1.1.1.1.1. Final decision | 2023-07-30 | 2023-07-30 | All |  | Done | bar: 2019-01-01 to 2019-01-06
1.2 github processing |  |  |  |  | 2023-07-29 | 2023-07-29 | Ruba | bar: 2019-01-01 to 2019-01-06
2. Editing | [8 empty] | Done
| 2.1 Edit Work Breakdown Structuren file |  |  |  | 2023-07-20 |  | Ruba |  | In-progress
|  | 2.1.1 Edit action plan file |  |  | 2023-07-29 | 2023-07-30 | Martada , Meshal |  | Done
3. Data | [8 empty] | In-progress
| 3.1 Data collection |  |  |  | 2023-08-01 | 2023-08-03 |  |  | In-progress
|  | 3.1.1 Data analysis |  |  | 2023-08-05 | 2023-08-06 |  |  | In-progress
4.Model | [8 empty] | In-progress
| 4.1 Model design | [7 empty] | In-progress
|  | 4.1.1 Model implementation | [6 empty] | In-progress
|  |  | 4.1.1.1 Model evaluation | [5 empty] | In-progress
In-progress
In-progress
These dates are illustrations
These status are illustrations